## CLI Commands
Title | CLI Commands
Issue
Assignee | Emanuel
Scenarios | Executed On | Status (Pass/Failed/Not Tested) | Results | Code Release Version | Comments | Linked issue (bug)
Pocket Accounts commands | 2021-02-24 | Passed. |  | RC-0.6.0
To build and sign a multisic tx | 2021-03-04 | Passed. |  | RC-0.6.0 |  | https://github.com/pokt-network/pocket-core/issues/1253
To create a new account | 2021-02-24 | Passed. | Account generated successfully: Address: 7cbd757f9c35d8d99dac0537d05f70cc6637b769 | RC-0.6.0
To create a multisig public key | 2021-02-24 | Passed. | Account generated successfully: Address: 7cbd757f9c35d8d99dac0537d05f70cc6637b769 | RC-0.6.0
To delete an existing account | 2021-02-24 | Passed. | Account deleted successfully | RC-0.6.0
To delete an existing account by providing wrong command format | 2021-02-24 | Passed. |  | RC-0.6.0
To export an existing account | 2021-02-24 | Passed. |  | RC-0.6.0
To export an existing account, and failing the passphrase | 2021-02-24 | Passed. |  | RC-0.6.0
To export an existing account, not provide the address | 2021-02-24 | Passed. |  | RC-0.6.0
To export an existing account with wrong address | 2021-02-24 | Passed. |  | RC-0.6.0
To export an existing plaintext private key | 2021-02-24 | Passed. |  | RC-0.6.0
To export an existing plaintext private key, providing wrong address | 2021-02-24 | Passed. |  | RC-0.6.0
To export an existing plaintext private key, providing incomplete command | 2021-02-24 | Passed. |  | RC-0.6.0
To get the validator address of an account | 2021-02-24 | Passed. |  | RC-0.6.0
To import a keypairs using armor | 2021-02-24 | Passed. |  | RC-0.6.0
To import a keypairs using armor, providing incomplete command | 2021-02-24 | Passed. |  | RC-0.6.0
To import raw private key | 2021-02-24 | Passed. |  | RC-0.6.0
To import raw private key, providing incomplete command | 2021-02-24 | Passed. |  | RC-0.6.0
To see the list of existing accounts | 2021-02-24 | Passed. |  | RC-0.6.0
To send raw transaction from signed bytes | 2021-02-24 | Passed. |  | RC-0.6.0
To send raw transaction from signed bytes, with incomplete command | 2021-02-24 | Passed. |  | RC-0.6.0
To send a POKT tx to a specific address | 2021-02-24 | Passed. |  | RC-0.6.0
To send a POKT tx to a specific address, missing commands | 2021-02-24 | Passed. |  | RC-0.6.0
To see the public key for an address | 2021-02-24 | Passed. |  | RC-0.6.0
To see the public key for an address, incomplete command. | 2021-02-24 | Passed. |  | RC-0.6.0
To sign a message with an account | 2021-02-24 | Passed. |  | RC-0.6.0
To sign a message with an account, missing commands | 2021-02-24 | Passed. |  | RC-0.6.0 | pocket-core accounts sign-ms-tx 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 d201db0b170d0a33a5e344a60a14154fa37d8b9c6b1343620fc02abcc3bb126cfaba1214448c23cd4f025ae76196c2b8dc5387990190474c1a0131120f0a0575706f6b7412063130303030301a7b0a31f325b8ad0a2bf325b8ad0a259d54477420c816e9195820e385f2895fcebf3e8087669ec9a863e4a31ebccbe5c96c7a02d01246b2f515f90a40c1138f847cbbf58b7efe7c3b8883ea43c84af140a161462c440a2086bb9b1f7ec7d5c1cafbf7828f3da2709 f325b8ad0a259d54477420c816e9195820e385f2895fcebf3e8087669ec9a863e4a31ebccbe5c96c7a02d0 pocket-testet-playground true
To sign a message with an account, incorrect text sintax | 2021-02-24 | Passed. |  | RC-0.6.0
To update existing account passphrase | 2021-02-24 | Passed. |  | RC-0.6.0
To update existing account passphrase, miss any of the passphrases | 2021-02-24 | Passed. |  | RC-0.6.0
To update existing account passphrase, missing address | 2021-02-24 | Passed. |  | RC-0.6.0
To show existing commands within the pocket app section | 2021-02-24 | Passed. |  | RC-0.6.0
To create an AAT | 2021-03-03 | Passed. | bash-5.0$ pocket-core apps create-aat 3174b558a3884b87cb6a68365892c5a26d18fe4c 3aa5afa3a35ab3e2b253516676dddb5b2b6f2f27ef9fe2f894483141dd765d6e key with address 3174b558a3884b87cb6a68365892c5a26d18fe4c not found | RC-0.6.0 | bash-5.0$ pocket-core apps create-aat 3174b558a3884b87cb6a68365892c5a26d18fe4c 3aa5afa3a35ab3e2b253516676dddb5b2b6f2f27ef9fe2f894483141dd765d6e Enter passphrase: { "version": "0.0.1", "app_pub_key": "3aa5afa3a35ab3e2b253516676dddb5b2b6f2f27ef9fe2f894483141dd765d6e", "client_pub_key": "3aa5afa3a35ab3e2b253516676dddb5b2b6f2f27ef9fe2f894483141dd765d6e", "signature": "4f35f2e6241a8e749d51649039c0009b161f44002c1fa94477d8589c44620676637b68c3df7779dcd7a2224567eead3e0c58da164f14d906525bd68757ae4c02" }
To create an AAT, with wrong APPaddress | 2021-02-24 | Passed. |  | RC-0.6.0
To create an AAT, with wrong clientPubKey | 2021-02-24 | Passed. |  | RC-0.6.0
To create an AAT, incomplete command | 2021-02-24 | Passed. |  | RC-0.6.0
To stake an APP in the network | 2021-02-24 | Passed. |  | RC-0.6.0
To stake an APP in the network, wrong address | 2021-02-24 | Passed. |  | RC-0.6.0
To stake an APP in the network, zero as amount | 2021-02-24 | Passed. |  | RC-0.6.0
To stake an APP in the network, wrong chains | 2021-02-24 | Passed. |  | RC-0.6.0
To stake an APP in the network, incomplete command | 2021-02-24 | Passed. |  | RC-0.6.0
To unstake an APP in the network | 2021-02-24 | Passed. |  | RC-0.6.0
To unstake an APP in the network, wrong address | 2021-02-24 | Passed. |  | RC-0.6.0
To unstake an APP in the network, incomplete command | 2021-02-24 | Passed. |  | RC-0.6.0
Pocket main commands | 2021-02-24 | Passed. |  | RC-0.6.0
To show existing commands within the pocket query section | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing account | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing account, wrong address | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing account, wrong height | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing account, incomplete command | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing account txs | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing account txs, wrong address | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing account txs, wrong proof | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing account txs, incomplete command | 2021-02-24 | Passed. |  | RC-0.6.0
To query current acl | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing app from address | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing app from address, wrong address | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing app from address, wrong height | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing app from address, incomplete command | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing app parameters | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing app parameters, wrong address | 2021-02-24 | Passed. |  | RC-0.6.0
To query the list of existing apps | 2021-02-24 | Passed. |  | RC-0.6.0
To query an address balance in the network | 2021-02-24 | Passed. |  | RC-0.6.0
To query an address balance in the network, wrong address | 2021-02-24 |  |  | RC-0.6.0
To query an address balance in the network, wrong height | 2021-02-24 |  |  | RC-0.6.0
To query an address balance in the network, incomplete command | 2021-02-24 |  |  | RC-0.6.0
To query a block's at height | 2021-02-24 | Failed. | http://localhost:8081/v1/query/block the http status code was not okay: 400, and the status was: 400 Bad Request, with a response of {"code":400,"message":"height must be greater than 0, but got 0"} | RC-0.6.0 | Command used: pocket-core query block (Then we should add the help information for missing a param)
To query a block's at height w/flags | 2021-02-24 | Failed. | http://localhost:8081/v1/query/block the http status code was not okay: 400, and the status was: 400 Bad Request, with a response of {"code":400,"message":"height must be greater than 0, but got 0"} | RC-0.6.0 | Command used: pocket-core query block (Then we should add the help information for missing a param)
To query a block's at height, incomplete | 2021-02-24 | Failed. | http://localhost:8081/v1/query/block the http status code was not okay: 400, and the status was: 400 Bad Request, with a response of {"code":400,"message":"height must be greater than 0, but got 0"} | RC-0.6.0 | Command used: pocket-core query block (Then we should add the help information for missing a param)
To query dao owner | 2021-02-24 | Passed. |  | RC-0.6.0
To query the chains height | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node from address | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node from address, wrong address | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node from address, wrong height | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node from address, incomplete command | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node claim | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node claim, wrong address | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node claim, wrong pub key | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node claim, invalid session height | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node claim, invalid claimType | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node claim, incomplete | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node claims | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node claims, wrong address | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node claims, incomplete | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node parameters | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node parameters, wrong address | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node receipt | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node receipt, wrong address | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node receipt, wrong pub key | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node receipt, invalid session height | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node receipt, invalid claimType | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node receipt, incomplete | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node receipts | 2021-02-24 | Passed. |  | RC-0.6.0
To query an existing node receipts, wrong address | 2021-02-24 | Passed. |  | RC-0.6.0
To query the list of existing nodes | 2021-02-24 | Passed. |  | RC-0.6.0
To query single param | 2021-02-24 | Passed. |  | RC-0.6.0 | We need to add help information for when missing a param.
To query the list of params | 2021-02-24 | Passed. |  | RC-0.6.0
To query the list of pocketcore params | 2021-02-24 | Passed. |  | RC-0.6.0
To get supplies | 2021-02-24 | Passed. |  | RC-0.6.0
To get existing supported networks | 2021-02-24 | Passed. |  | RC-0.6.0
To get transactions based on the hash | 2021-02-24 | Passed. |  | RC-0.6.0
To get transactions based on the hash, wrong hash | 2021-02-24 | Passed. |  | RC-0.6.0
To get transactions based on the hash, incomplete commands | 2021-02-24 | Passed. |  | RC-0.6.0
To query the latest upgrade | 2021-02-24 | Passed. |  | RC-0.6.0
User wants to reset his pocket config | 2021-02-24 | Passed. |  | RC-0.6.0
User wants to start pocket | 2021-02-24 | Passed. |  | RC-0.6.0
User wants to see the utilities within pocket | 2021-02-24 | Passed. |  | RC-0.6.0
Generate completion script | 2021-02-24 | Passed. |  | RC-0.6.0
Decodes a given transaction encoded in Amino/Proto base64 bytes | 2021-02-24 | Passed. |  | RC-0.6.0
Delete chains file | 2021-02-24 | Passed. |  | RC-0.6.0
exports new genesis based on state | 2021-02-24 | Passed. |  | RC-0.6.0
Prints Default config.json to console | 2021-02-24 | Passed. |  | RC-0.6.0
Rollbacks the blockchain, the state, and app to a previous height | 2021-02-24 | Passed. |  | RC-0.6.0
Updates config.json file | 2021-02-24 | Passed. |  | RC-0.6.0
User wants to generate a chain identifier | 2021-02-24 | Passed. |  | RC-0.6.0
User wants to generate a chain identifier, wrong ticker | 2021-02-24 | Passed. |  | RC-0.6.0
User wants to see the pocket version | 2021-02-24 | Passed. |  | RC-0.6.0
To show existing commands within the pocket nodes section | 2021-02-24 | Passed. |  | RC-0.6.0
To stake an node in the network | 2021-02-24 | Passed. |  | RC-0.6.0
To stake an node in the network, wrong address | 2021-02-24 | Passed. |  | RC-0.6.0
To stake a nodes in the network, amount lower than minimum stake | 2021-02-24 | Passed. |  | RC-0.6.0
To stake a nodes in the network, wrong serviceURI | 2021-02-24 | Passed. |  | RC-0.6.0
To stake a node in the network, incomplete command | 2021-02-24 | Passed. |  | RC-0.6.0
To unjail a node in the network | 2021-02-24 | Passed. |  | RC-0.6.0
To unjail a node in the network, wrong address | 2021-02-24 | Passed. |  | RC-0.6.0
To unjail a node in the network, incomplete command | 2021-02-24 | Passed. |  | RC-0.6.0
To unstake a node in the network | 2021-02-24 | Passed. |  | RC-0.6.0
To unstake a node in the network, wrong address | 2021-02-24 | Passed. |  | RC-0.6.0
To unstake a node in the network, incomplete command | 2021-02-24 | Passed. |  | RC-0.6.0
To stop the pocket process | 2021-02-24 | Passed. |  | RC-0.6.0

## Leader election and distributio
Title | Leader election and distribution overtime
Issue
Assignee | Emanuel
Scenarios | Executed On | Status (Pass/Failed/Not Tested) | Results | Code Release Version | Comments | Linked issue (bug)
Same power validators | 2021-02-24 | Passed. |  | RC-0.6.0
Different Validator stake | 2021-02-24 | Passed. |  | RC-0.6.0

## SendRawStakeUnstakeUnjail
Title | Send/Raw/Stake/Unstake/Unjail
Issue
Assignee | Emanuel
Scenarios | Executed On | Status (Pass/Failed/Not Tested) | Results | Code Release Version | Comments | Linked issue (bug)
Apps stake | 2021-03-03 | Passed. |  | RC-0.6.0
Apps unstake | 2021-03-03 | Passed. |  | RC-0.6.0
Unstaked a node that's not staked | 2021-02-24 | Passed. |  | RC-0.6.0
unstake a node that doesn't exist | 2021-02-24 | Passed. |  | RC-0.6.0
Shouldn't stake a nonexistent app | 2021-02-24 | Passed. |  | RC-0.6.0
Shouldn't stake a nonexistent node | 2021-02-24 | Passed. |  | RC-0.6.0
Staking node with insufficient founds | 2021-02-24 | Passed. |  | RC-0.6.0
Staking app with insufficient founds | 2021-02-24 | Passed. |  | RC-0.6.0
Shouldn't stake a nonexistent node | 2021-02-24 | Passed. |  | RC-0.6.0
Staking node with insufficient founds | 2021-02-24 | Passed. |  | RC-0.6.0
Staking app with insufficient founds | 2021-02-24 | Passed. |  | RC-0.6.0
Validator misses X blocks | 2021-02-24 | Passed. |  | RC-0.6.0
unjail node from genesis | 2021-02-24 | Passed. |  | RC-0.6.0
force node unstake | 2021-02-24 | Passed. |  | RC-0.6.0
Apps stake | 2021-02-24 | Passed. |  | RC-0.6.0
Start with Jailed node | 2021-02-24 | Passed. |  | RC-0.6.0
Apps unstake | 2021-02-24 | Passed. |  | RC-0.6.0
Ujail node | 2021-02-24 | Passed. |  | RC-0.6.0
Node Stake | 2021-02-24 | Passed. |  | RC-0.6.0
Node Unstake | 2021-02-24 | Passed. |  | RC-0.6.0
Shouldn't unstake a nonexistent app | 2021-02-24 | Passed. |  | RC-0.6.0
Shouldn't unstake a nonexistent app | 2021-02-24 | Passed. |  | RC-0.6.0
Unstaked a node that's not staked | 2021-02-24 | Passed. |  | RC-0.6.0
unstake a node that doesn't exist | 2021-02-24 | Passed. |  | RC-0.6.0
Shouldn't stake a nonexistent app | 2021-02-24 | Passed. |  | RC-0.6.0

## Multi-signature Accounts
Title | Multi-signature accounts
Issue | https://github.com/pokt-network/pocket-core/issues/1243
Assignee | Emanuel
Scenarios | Executed On | Status (Pass/Failed/Not Tested) | Results | Code Release Version | Comments | Linked issue (bug)
create multi signature account | 2021-03-03 | Passed. |  | RC-0.6.0 | bash-5.0$ pocket-core accounts create-multi-public c816e9195820e385f2895fcebf3e8087669ec9a863e4a31ebccbe5c96c7a02d0 Sucessfully generated Multisig Public Key: f325b8ad0a259d54477420c816e9195820e385f2895fcebf3e8087669ec9a863e4a31ebccbe5c96c7a02d0 With Address: CD6232372232BFF1ADCA5E2CC5C7764168C6CF71
create multi signature account, invalid character | 2021-03-04 | Passed. |  | RC-0.6.0 | bash-5.0$ pocket-core accounts build-MS-Tx 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 "{\"type\":\"pos\/Send\",\"value\":{\"from_address\":\"154fa37d8b9c6b1343620fc02abcc3bb126cfaba\",\"to_address\":\"448c23cd4f025ae76196c2b8dc5387990190474c\",\"amount\":\"1\"}}" f325b8ad0a259d54477420c816e9195820e385f2895fcebf3e8087669ec9a863e4a31ebccbe5c96c7a02d0 testnet 100000 true Enter passphrase: Multisig transaction: d201db0b170d0a33a5e344a60a14154fa37d8b9c6b1343620fc02abcc3bb126cfaba1214448c23cd4f025ae76196c2b8dc5387990190474c1a0131120f0a0575706f6b7412063130303030301a7b0a31f325b8ad0a2bf325b8ad0a259d54477420c816e9195820e385f2895fcebf3e8087669ec9a863e4a31ebccbe5c96c7a02d01246b2f515f90a40c1138f847cbbf58b7efe7c3b8883ea43c84af140a161462c440a2086bb9b1f7ec7d5c1cafbf7828f3da2709f02a89ea09541b393409e3f9b21ae4f690124ee032890fdb5a087a0e8b0c401 | https://github.com/pokt-network/pocket-core/issues/1253
build a multi-signature transaction | 2021-03-04 | Passed. |  | RC-0.6.0 | Command used (leacyCodec true or false): pocket-core accounts build-MS-Tx 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 "{\"type\":\"pos\/Send\",\"value\":{\"from_address\":\"154fa37d8b9c6b1343620fc02abcc3bb126cfaba\",\"to_address\":\"448c23cd4f025ae76196c2b8dc5387990190474c\",\"amount\":\"1\"}}" 0b7477e98009ce1f8815a05fe5d01bcd9f14295a8d2a3e72bfd5cd215692d86d testnet 100000 true
Sign a multi-signature transaction | 2021-02-24 | Passed. |  | RC-0.6.0
Sign a multi-signature transaction next | 2021-02-24 | Passed. |  | RC-0.6.0
create multi signature account | 2021-03-04 | Passed. |  | RC-0.6.0
create multi signature account, invalid character | 2021-03-04 | Passed. |  | RC-0.6.0
build a multi-signature transaction | 2021-03-04 | Passed. |  | RC-0.6.0
Sign a multi-signature transaction | 2021-02-24 | Passed. |  | RC-0.6.0
Sign a multi-signature transaction next | 2021-02-24 | Passed. |  | RC-0.6.0

## Queries RPCCLI
Title | Queries RPC/CLI
Issue | https://github.com/pokt-network/pocket-core/issues/1243
Assignee | Emanuel
Scenarios | Executed On | Status (Pass/Failed/Not Tested) | Results | Code Release Version | Comments | Linked issue (bug)
Account method in pocket-core cli's query namespace | 2021-02-25 | Passed. |  | RC-0.6.0
Invalid height | 2021-02-25 | Passed. |  | RC-0.6.0
Account does not exist | 2021-02-25 | Passed. |  | RC-0.6.0
Account address is invalid | 2021-02-25 | Passed. |  | RC-0.6.0
Account address contains invalid characters | 2021-02-25 | Passed. |  | RC-0.6.0
Returns transactions | 2021-02-25 | Passed. |  | RC-0.6.0
Returns null | 2021-02-25 | Passed. |  | RC-0.6.0
Invalid chars in address | 2021-02-25 | Passed. |  | RC-0.6.0
ACL method in pocket-core cli's query namespace | 2021-02-25 | Passed. |  | RC-0.6.0
Request valid app height. | 2021-02-25 | Passed. |  | RC-0.6.0
Request invalid app height. | 2021-02-25 | Passed. |  | RC-0.6.0
Request invalid app height with bad chars. | 2021-02-25 | Passed. |  | RC-0.6.0
Returns app details | 2021-02-25 | Passed. |  | RC-0.6.0
Application address doesn't exist | 2021-02-25 | Passed. |  | RC-0.6.0
Application address has incorrect length valid | 2021-02-25 | Passed. |  | RC-0.6.0
Application address has invalid characters | 2021-02-25 | Passed. |  | RC-0.6.0
Returns balance of existing account | 2021-02-25 | Passed. |  | RC-0.6.0
Can't return balance of account that doesn't exist | 2021-02-25 | Passed. |  | RC-0.6.0
Get block height | 2021-02-25 | Passed. |  | RC-0.6.0
Given an invalid number height | 2021-02-25 | Passed. |  | RC-0.6.0
Given an invalid char in height | 2021-02-25 | Passed. |  | RC-0.6.0
Returns a block height | 2021-02-25 | Passed. |  | RC-0.6.0
Given an invalid number height | 2021-02-25 | Passed. |  | RC-0.6.0
Given an invalid char in height | 2021-02-25 | Passed. |  | RC-0.6.0
Get daoOwner | 2021-02-25 | Passed. |  | RC-0.6.0
Returns the height of the pocket core network | 2021-02-25 | Passed. |  | RC-0.6.0
Correct height number | 2021-02-25 | Passed. |  | RC-0.6.0
Incorrect height number | 2021-02-25 | Passed. |  | RC-0.6.0
Invalid height number | 2021-02-25 | Passed. |  | RC-0.6.0
Pocket node exists | 2021-02-25 | Passed. |  | RC-0.6.0
Node information is invalid | 2021-02-25 | Passed. |  | RC-0.6.0
Return list of all relay batch proofs submitted by node | 2021-02-25 | Passed. |  | RC-0.6.0
Returns null for non existent receipts | 2021-02-25 | Passed. |  | RC-0.6.0
Returns null for non existent node | 2021-02-25 | Passed. |  | RC-0.6.0
Returns a pocket network node at the specified height | 2021-02-25 | Passed. |  | RC-0.6.0
Node doesn't exist in pocket core network | 2021-02-25 | Passed. |  | RC-0.6.0
Node address with invalid chars | 2021-02-25 | Passed. |  | RC-0.6.0
Returns page of nodes | 2021-02-25 | Passed. |  | RC-0.6.0
Returns error when given wrong height | 2021-02-25 | Passed. |  | RC-0.6.0
Returns null when given 0 page | 2021-02-25 | Passed. |  | RC-0.6.0
Return supported blockchains at given height | 2021-02-25 | Passed. |  | RC-0.6.0
Return error with incorrect height | 2021-02-25 | Passed. |  | RC-0.6.0
Returns the list of node params specified in the height | 2021-02-25 | Passed. |  | RC-0.6.0
Returns error code with wrong height | 2021-02-25 | Passed. |  | RC-0.6.0
Returns list of supported blockchains specified in the height | 2021-02-25 | Passed. |  | RC-0.6.0
Returns an error code with invalid height | 2021-02-25 | Passed. |  | RC-0.6.0
Return a transaction detail | 2021-02-25 | Passed. |  | RC-0.6.0
Transaction doesn't exist | 2021-02-25 | Passed. |  | RC-0.6.0
Transaction has invalid characters | 2021-02-25 | Passed. |  | RC-0.6.0
Gets the latest gov upgrade | 2021-02-25 | Passed. |  | RC-0.6.0
Send invalid height | 2021-02-25 | Passed. |  | RC-0.6.0
RPCs | 2021-02-25
Account method in pocket-core cli's query namespace | 2021-02-25 | Passed. |  | RC-0.6.0
Invalid height | 2021-02-25 | Passed. |  | RC-0.6.0
Account does not exist | 2021-02-25 | Passed. |  | RC-0.6.0
Account address is invalid | 2021-02-25 | Passed. |  | RC-0.6.0
Account address contains invalid characters | 2021-02-25 | Passed. |  | RC-0.6.0
Returns transactions | 2021-02-25 | Passed. |  | RC-0.6.0
Returns null | 2021-02-25 | Passed. |  | RC-0.6.0
Invalid chars in address | 2021-02-25 | Passed. |  | RC-0.6.0
ACL method in pocket-core cli's query namespace | 2021-02-25 | Passed. |  | RC-0.6.0
Request valid app height. | 2021-02-25 | Passed. |  | RC-0.6.0
Request invalid app height. | 2021-02-25 | Passed. |  | RC-0.6.0
Request invalid app height with bad chars. | 2021-02-25 | Passed. |  | RC-0.6.0
Returns app details | 2021-02-25 | Passed. |  | RC-0.6.0
Application address doesn't exist | 2021-02-25 | Passed. |  | RC-0.6.0
Application address has incorrect length valid | 2021-02-25 | Passed. |  | RC-0.6.0
Application address has invalid characters | 2021-02-25 | Passed. |  | RC-0.6.0
Returns balance of existing account | 2021-02-25 | Passed. |  | RC-0.6.0
Can't return balance of account that doesn't exist | 2021-02-25 | Passed. |  | RC-0.6.0
Get block height | 2021-02-25 | Passed. |  | RC-0.6.0
Given an invalid number height | 2021-02-25 | Passed. |  | RC-0.6.0
Given an invalid char in height | 2021-02-25 | Passed. |  | RC-0.6.0
Returns a block height | 2021-02-25 | Passed. |  | RC-0.6.0
Given an invalid number height | 2021-02-25 | Passed. |  | RC-0.6.0
Given an invalid char in height | 2021-02-25 | Passed. |  | RC-0.6.0
Get daoOwner | 2021-02-25 | Passed. |  | RC-0.6.0
Returns the height of the pocket core network | 2021-02-25 | Passed. |  | RC-0.6.0
Correct height number | 2021-02-25 | Passed. |  | RC-0.6.0
Incorrect height number | 2021-02-25 | Passed. |  | RC-0.6.0
Invalid height number | 2021-02-25 | Passed. |  | RC-0.6.0
Pocket node exists | 2021-02-25 | Passed. |  | RC-0.6.0
Node information is invalid | 2021-02-25 | Passed. |  | RC-0.6.0
Return list of all relay batch proofs submitted by node | 2021-02-25 | Passed. |  | RC-0.6.0
Returns null for non existent receipts | 2021-02-25 | Passed. |  | RC-0.6.0
Returns null for non existent node | 2021-02-25 | Passed. |  | RC-0.6.0
Returns a pocket network node at the specified height | 2021-02-25 | Passed. |  | RC-0.6.0
Node doesn't exist in pocket core network | 2021-02-25 | Passed. |  | RC-0.6.0
Node address with invalid chars | 2021-02-25 | Passed. |  | RC-0.6.0
Returns page of nodes | 2021-02-25 | Passed. |  | RC-0.6.0
Returns error when given wrong height | 2021-02-25 | Passed. |  | RC-0.6.0
Returns null when given 0 page | 2021-02-25 | Passed. |  | RC-0.6.0
Return supported blockchains at given height | 2021-02-25 | Passed. |  | RC-0.6.0
Return error with incorrect height | 2021-02-25 | Passed. |  | RC-0.6.0
Returns the list of node params specified in the height | 2021-02-25 | Passed. |  | RC-0.6.0
Returns error code with wrong height | 2021-02-25 | Passed. |  | RC-0.6.0
Returns list of supported blockchains specified in the height | 2021-02-25 | Passed. |  | RC-0.6.0
Returns an error code with invalid height | 2021-02-25 | Passed. |  | RC-0.6.0
Return a transaction detail | 2021-02-25 | Passed. |  | RC-0.6.0
Transaction doesn't exist | 2021-02-25 | Passed. |  | RC-0.6.0
Transaction has invalid characters | 2021-02-25 | Passed. |  | RC-0.6.0
Gets the latest gov upgrade | 2021-02-25 | Passed. |  | RC-0.6.0
Send invalid height | 2021-02-25 | Passed. |  | RC-0.6.0

## DispatchRelayChallenge RPC
Title | Disptach/Relay/Challenge RPC
Issue | https://github.com/pokt-network/pocket-core/issues/1243
Assignee | Emanuel
Scenarios | Executed On | Status (Pass/Failed/Not Tested) | Results | Code Release Version | Comments | Linked issue (bug)
Sends request to check dispatch that will be servicing your requests for the session. | 2021-02-25 | Passed. |  | RC-0.6.0
Given a transaction, the relay should send that transaction and respond with the correct message of success | 2021-02-25 | Passed. |  | RC-0.6.0
User Submits Challenge Request | 2021-02-25 | Passed. |  | RC-0.6.0
Challenge Transaction submitted to the network | 2021-02-25 | Passed. |  | RC-0.6.0
User Submits Challenge Request without majority proof | 2021-02-25 | Passed. |  | RC-0.6.0
Given a transaction, the relay should send that transaction and respond with the correct message of success | 2021-02-25 | Passed. |  | RC-0.6.0
chains.json contains url with self signed cert | 2021-02-25 | Passed. |  | RC-0.6.0

## Economics
Title | Economics
Issue | https://github.com/pokt-network/pocket-core/issues/1243
Assignee | Emanuel
Scenarios | Executed On | Status (Pass/Failed/Not Tested) | Results | Code Release Version | Comments | Linked issue (bug)
Block Proposer Reward | 2021-02-25 | Passed. |  | RC-0.6.0
Challenge burn | 2021-02-25 | Passed. |  | RC-0.6.0
Relay rewards | 2021-02-25 | Passed. |  | RC-0.6.0
Downtime burn | 2021-02-25 | Passed. |  | RC-0.6.0

## Minimum Viable Gov
Title | Minium Viable Governance
Issue | https://github.com/pokt-network/pocket-core/issues/1243
Assignee | Emanuel
Scenarios | Executed On | Status (Pass/Failed/Not Tested) | Results | Code Release Version | Comments | Linked issue (bug)
Change param pocketcore/ClaimExpiration | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov change_param 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 pocket-testet-playground pocketcore/ClaimExpiration \"10\" 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "7186694F7A318BEAAA58A9B824AF4FEF2F930A08B800EF34492F05E11573E4AA" }
Change param pocketcore/MinimumNumberOfProofs | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov change_param 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 pocket-testet-playground pocketcore/MinimumNumberOfProofs \"3\" 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "BE1EB8F4C7702D1FE428B8772F9A8803FAC28F53F133FF1CB5B28FE4910C04CD" }
Change param pocketcore/SessionNodeCount | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov change_param 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 pocket-testet-playground pocketcore/SessionNodeCount \"3\" 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "0C5A49E26B262849E4B7981761F504681B925F3E194C9D9D30B07C13970A8687" }
Change param pocketcore/ReplayAttackBurnMultiplier | 2021-02-25 | Passed. | ./pocket_core gov change_param 9bc2a4e9aa704f2b9677ff60033a0d579b6dee4c pocket-test pocketcore/ReplayAttackBurnMultiplier \"2\" 10000 Enter Password: http://localhost:8081/v1/client/rawtx { "height": "0", "logs": [ { "events": [ { "attributes": [ { "key": "action", "value": "change_param" } ], "type": "message" } ], "log": "", "msg_index": 0, "success": true } ], "raw_log": "[{\"msg_index\":0,\"success\":true,\"log\":\"\",\"events\":[{\"type\":\"message\",\"attributes\":[{\"key\":\"action\",\"value\":\"change_param\"}]}]}]", "txhash": "4ECF3292E6007BA84B2E62476EDAAB3D0E361073C6C9427861B610BC1B0105E8" }
Change param pocketcore/ClaimSubmissionWindow | 2021-02-25 | Passed. | ./pocket_core gov change_param 9bc2a4e9aa704f2b9677ff60033a0d579b6dee4c pocket-test pocketcore/ClaimSubmissionWindow \"1\" 10000 Enter Password: http://localhost:8081/v1/client/rawtx { "height": "0", "logs": [ { "events": [ { "attributes": [ { "key": "action", "value": "change_param" } ], "type": "message" } ], "log": "", "msg_index": 0, "success": true } ], "raw_log": "[{\"msg_index\":0,\"success\":true,\"log\":\"\",\"events\":[{\"type\":\"message\",\"attributes\":[{\"key\":\"action\",\"value\":\"change_param\"}]}]}]", "txhash": "5C21C921CF6C0457320412536677882766F2D32B7B9D3B5494AD48037B0768DE" }
Change param pocketcore/SupportedBlockchains | 2021-02-25 | Passed. | ./pocket_core gov change_param 9bc2a4e9aa704f2b9677ff60033a0d579b6dee4c pocket-test pocketcore/SupportedBlockchains "[\"00\",\"01\"]" 10000 Enter Password: http://localhost:8081/v1/client/rawtx { "height": "0", "logs": [ { "events": [ { "attributes": [ { "key": "action", "value": "change_param" } ], "type": "message" } ], "log": "", "msg_index": 0, "success": true } ], "raw_log": "[{\"msg_index\":0,\"success\":true,\"log\":\"\",\"events\":[{\"type\":\"message\",\"attributes\":[{\"key\":\"action\",\"value\":\"change_param\"}]}]}]", "txhash": "BA4D49DC6A91D44537081161FA2893648964850257526CBA2E7F5243C7816D4C" }
Change param pos/DAOAllocation | 2021-02-25 | Passed. | ./pocket_core gov change_param 9bc2a4e9aa704f2b9677ff60033a0d579b6dee4c pocket-test pos/DAOAllocation \"9\" 10000 Enter Password: http://localhost:8081/v1/client/rawtx { "height": "0", "logs": [ { "events": [ { "attributes": [ { "key": "action", "value": "change_param" } ], "type": "message" } ], "log": "", "msg_index": 0, "success": true } ], "raw_log": "[{\"msg_index\":0,\"success\":true,\"log\":\"\",\"events\":[{\"type\":\"message\",\"attributes\":[{\"key\":\"action\",\"value\":\"change_param\"}]}]}]", "txhash": "59689BBCC98FFF9807CE5B9A8B60AE4B29EB36D3DCFC8A26241BC8F0F37DBE92" }
Change param pos/DowntimeJailDuration | 2021-02-25 | Passed. | ./pocket_core gov change_param 9bc2a4e9aa704f2b9677ff60033a0d579b6dee4c pocket-test pos/DowntimeJailDuration \"7000000\" 10000 Enter Password: http://localhost:8081/v1/client/rawtx { "height": "0", "logs": [ { "events": [ { "attributes": [ { "key": "action", "value": "change_param" } ], "type": "message" } ], "log": "", "msg_index": 0, "success": true } ], "raw_log": "[{\"msg_index\":0,\"success\":true,\"log\":\"\",\"events\":[{\"type\":\"message\",\"attributes\":[{\"key\":\"action\",\"value\":\"change_param\"}]}]}]", "txhash": "08AF71A0CF322B0B690CC9E25484C58908CCACA6E0645A1CF7B4DA8C52D45F9B" }
Change param pos/MaxEvidenceAge | 2021-02-25 | Passed. | ./pocket_core gov change_param 9bc2a4e9aa704f2b9677ff60033a0d579b6dee4c pocket-test pos/MaxEvidenceAge \"76500000\" 10000 Enter Password: http://localhost:8081/v1/client/rawtx { "height": "0", "logs": [ { "events": [ { "attributes": [ { "key": "action", "value": "change_param" } ], "type": "message" } ], "log": "", "msg_index": 0, "success": true } ], "raw_log": "[{\"msg_index\":0,\"success\":true,\"log\":\"\",\"events\":[{\"type\":\"message\",\"attributes\":[{\"key\":\"action\",\"value\":\"change_param\"}]}]}]", "txhash": "4CFB6BB714F18092F045B4611E8E9C6AB32D91B46F99C0BDC9FA25AA7BAB0288" }
Change param pos/MaxJailedBlocks | 2021-02-25 | Passed. | ./pocket_core gov change_param 9bc2a4e9aa704f2b9677ff60033a0d579b6dee4c pocket-test pos/MaxJailedBlocks \"7000\" 10000 Enter Password: http://localhost:8081/v1/client/rawtx { "height": "0", "logs": [ { "events": [ { "attributes": [ { "key": "action", "value": "change_param" } ], "type": "message" } ], "log": "", "msg_index": 0, "success": true } ], "raw_log": "[{\"msg_index\":0,\"success\":true,\"log\":\"\",\"events\":[{\"type\":\"message\",\"attributes\":[{\"key\":\"action\",\"value\":\"change_param\"}]}]}]", "txhash": "BA7C4EFDACB8C32C82C1F418E2F4F7627B5A6F64491BF7648CD10FE864055C0F" }
Change param pos/MaxValidators | 2021-02-25 | Passed. | ./pocket_core gov change_param 9bc2a4e9aa704f2b9677ff60033a0d579b6dee4c pocket-test pos/MaxValidators \"7000\" 10000 Enter Password: http://localhost:8081/v1/client/rawtx { "height": "0", "logs": [ { "events": [ { "attributes": [ { "key": "action", "value": "change_param" } ], "type": "message" } ], "log": "", "msg_index": 0, "success": true } ], "raw_log": "[{\"msg_index\":0,\"success\":true,\"log\":\"\",\"events\":[{\"type\":\"message\",\"attributes\":[{\"key\":\"action\",\"value\":\"change_param\"}]}]}]", "txhash": "2C08853DFF2C954CC8D40C7CC8D51F1CB457979E5036B971EBA6ABA9120A12D4" }
Change param pos/MaximumChains | 2021-02-25 | Passed. | ./pocket_core gov change_param 9bc2a4e9aa704f2b9677ff60033a0d579b6dee4c pocket-test pos/MaximumChains \"7\" 10000 Enter Password: http://localhost:8081/v1/client/rawtx { "height": "0", "logs": [ { "events": [ { "attributes": [ { "key": "action", "value": "change_param" } ], "type": "message" } ], "log": "", "msg_index": 0, "success": true } ], "raw_log": "[{\"msg_index\":0,\"success\":true,\"log\":\"\",\"events\":[{\"type\":\"message\",\"attributes\":[{\"key\":\"action\",\"value\":\"change_param\"}]}]}]", "txhash": "1E28F4FF7C8FCA59FC03EC2DEF26B54197C33CA7C55DECFF877FF866BE019C24" }
Change param pos/MinSignedPerWindow | 2021-02-25 | Passed. | ./pocket_core gov change_param 9bc2a4e9aa704f2b9677ff60033a0d579b6dee4c pocket-test pos/MinSignedPerWindow \"0.800\" 10000 Enter Password: http://localhost:8081/v1/client/rawtx { "height": "0", "logs": [ { "events": [ { "attributes": [ { "key": "action", "value": "change_param" } ], "type": "message" } ], "log": "", "msg_index": 0, "success": true } ], "raw_log": "[{\"msg_index\":0,\"success\":true,\"log\":\"\",\"events\":[{\"type\":\"message\",\"attributes\":[{\"key\":\"action\",\"value\":\"change_param\"}]}]}]", "txhash": "948978E2A4500B32106F3B1A8B1072F5861612CA6757EF3035FD2476C83CE229" }
Change param pos/ProposerPercentage | 2021-02-25 | Passed. | ./pocket_core gov change_param 9bc2a4e9aa704f2b9677ff60033a0d579b6dee4c pocket-test pos/ProposerPercentage \"2\" 10000 Enter Password: http://localhost:8081/v1/client/rawtx { "height": "0", "logs": [ { "events": [ { "attributes": [ { "key": "action", "value": "change_param" } ], "type": "message" } ], "log": "", "msg_index": 0, "success": true } ], "raw_log": "[{\"msg_index\":0,\"success\":true,\"log\":\"\",\"events\":[{\"type\":\"message\",\"attributes\":[{\"key\":\"action\",\"value\":\"change_param\"}]}]}]", "txhash": "62BC44F8CC981B34AD12BA0E2EEC93D8DDE92AFCB878C0BDA184BDB6012D617D" }
Change param pos/RelaysToTokensMultiplier | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov change_param 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 pocket-testet-playground pocketcore/RelaysToTokensMultiplier \"2000\" 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "0A5D1C0A03B090490A5A07D2EA39307D430508139F24D9EB058E0D436A1FCC56" }
Change param pos/BlocksPerSession | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov change_param 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 pocket-testet-playground pocketcore/BlocksPerSession \"13\" 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "4BCABDEFDEE62D139067AB5D052DD82927A02D7E5C9F3D85985E79D5DF975911" }
Change param pos/SignedBlocksWindow | 2021-03-02 | Passed. | ash-5.0$ pocket-core gov change_param 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 pocket-testet-playground pocketcore/SignedBlocksWindow \"95\" 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "C2A944FD874EE279D2B11F42CC6F0F48726A57EFAD34B0BAEAF4861FD225D7CB" }
Change param pos/SlashFractionDoubleSign | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov change_param 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 pocket-testet-playground pocketcore/SlashFractionDoubleSign \"0.0666\" 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "D5C4872FA253B98917E6A3EABEAD0E786C6CAF9CE143187BA746E8CCFD4F681D" }
Change param pos/SlashFractionDowntime | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov change_param 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 pocket-testet-playground pocketcore/SlashFractionDowntime \"0.02\" 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "A301B61F1655B49D34461E9C46AE33F4B0A916EC5B810391018F2E350482E28E" }
Change param pos/StakeMinimum | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov change_param 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 pocket-testet-playground pocketcore/StakeMinimum \"1200000\" 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "149B7E4FA651BEA0CBB6D1F00B574F6841A8BEE1F06DB62CE62F50177D3FB61A" }
Change param pos/UnstakingTime | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov change_param 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 pocket-testet-playground pocketcore/UnstakingTime \"1530000\" 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "262C5CBC8162547F38905FD600B2EC09513F9BC2DA1AC7EA396B2465D7B311FE" }
Change param application/AppUnstakingTime | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov change_param 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 pocket-testet-playground pocketcore/AppUnstakingTime \"1530000\" 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "31206C258795063655A51C19B034D81DEA04ECEA9912036E266352762BDDAC19" }
Change param application/MaxApplications | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov change_param 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 pocket-testet-playground pocketcore/MaxApplications \"15300\" 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "24A01645F1ED4CEE13801A4A5F37393BE48FB8B0A31CAD98B358F099483E7F4A" }
Change param application/MaximumChains | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov change_param 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 pocket-testet-playground pocketcore/MaximumChains \"20\" 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "30DF953542A4AF3848AD4AE929A38000E7E4CD301B87628356638F94F9629B78" }
Change param application/ApplicationStakeMinimum | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov change_param 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 pocket-testet-playground pocketcore/ApplicationStakeMinimum \"900000\" 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "14009FE9E3F67CBE94CD3CD4C0DA0852C7A2AE59879E56036313559A5AA92EF4" }
Change param application/BaseRelaysPerPOKT | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov change_param 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 pocket-testet-playground pocketcore/BaseRelaysPerPOKT \"900\" 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "75508C8E89A5E95DAE8F794C960641C96078B0E9766F8599B13D51AD10046D39" }
Change param application/StabilityAdjustment | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov change_param 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 pocket-testet-playground pocketcore/StabilityAdjustment \"1\" 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "61AB4C16863D892B241AC5C98CF1C6F854C10DE653332212BDBEE5656AE129D3" }
Change param application/ParticipationRateOn | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov change_param 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 pocket-testet-playground pocketcore/ParticipationRateOn false/true 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "DB2E3E73C86B6285A9C3C4F56404431E7179B61E834E0FAF13E82C95A41907D3" }
Transfer funds from DAO | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov transfer 100 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 a023d0b551cf6bafa1fbff9537d0eea288d67dd0 pocket-testet-playground 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "40E5E5A203EAFB0492503DDD7478677926167C8F1BCEDB13FF9D70DB6485949C" } bash-5.0$ pocket-core query balance a023d0b551cf6bafa1fbff9537d0eea288d67dd0 http://localhost:8081/v1/query/balance { "balance": 100 }
Burn funds from DAO | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov burn 100 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 a023d0b551cf6bafa1fbff9537d0eea288d67dd0 pocket-testet-playground 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "2CB437F674656638FFEAA6B47BFCB7FEFECE46E29AAAE9472A66EB3B06911C2D" }
Upgrade protocol | 2021-03-02 | Passed. | bash-5.0$ pocket-core gov upgrade 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 191 "6.0" pocket-testet-playground 10000 false Enter Password: http://localhost:8081/v1/client/rawtx { "logs": null, "txhash": "2706E8EEF4CBB7A7A91DE402A868D16AC47562A029F4F090ECB596B8EF868368" }

## LegacyCodec Tests
Title | LegacyCodec
Issue | https://github.com/pokt-network/pocket-core/issues/1243
Assignee | Emanuel
Scenarios | Executed On | Status (Pass/Failed/Not Tested) | Results | Code Release Version | Comments | Linked issue (bug)
Make sure that existing functionality it's still working | 2021-03-02 | Passed.
Send a transaction using amino encoding | 2021-03-02 | Passed.
Send a transaction using defaulted proto encoding | 2021-03-02 | Passed.
Build and sign a multisignature using amino encoding | 2021-03-04 | Passed. | Refer to Multi-signature accounts sheet or CLI Commands sheet - row 6, for more details
Build and sign a multisignature using defaulted proto encoding | 2021-03-04 | Passed. | Refer to Multi-signature accounts sheet or CLI Commands sheet - row 6, for more details
Sign a multisignature with public keys using amino encoding | 2021-03-04 | Passed. | Refer to Multi-signature accounts sheet or CLI Commands sheet - row 6, for more details
Sign a multisignature with public keys using defaulted proto encoding | 2021-03-04 | Passed. | Refer to Multi-signature accounts sheet or CLI Commands sheet - row 6, for more details
Sign a multisignature transaction object, result is hex encoded standard using amino encoding | 2021-03-04 | Passed. | Refer to Multi-signature accounts sheet or CLI Commands sheet - row 6, for more details
Sign a multisignature transaction object, result is hex encoded standard using defaulted proto encoding | 2021-03-04 | Passed. | Refer to Multi-signature accounts sheet or CLI Commands sheet - row 6, for more details
Stake an APP, using amino encoding | 2021-03-02 | Passed.
Stake an APP, using defaulted proto encoding | 2021-03-02 | Passed.
Unstake an APP, using amino encoding | 2021-03-02 | Passed.
Unstake an APP, using defaulted proto encoding | 2021-03-02 | Passed.
Stake a node, using amino encoding | 2021-03-02 | Passed.
Stake a node, using defaulted proto encoding | 2021-03-02 | Passed.
Unstake a node, using amino encoding | 2021-03-02 | Passed.
Unstake a node, using defaulted proto encoding | 2021-03-02 | Passed.
Unjail a node, using amino encoding | 2021-03-02 | Passed.
Unjail a node, using defaulted proto encoding | 2021-03-02 | Passed.
Unjail a node, using amino encoding | 2021-03-02 | Passed.
Unjail a node, using defaulted proto encoding | 2021-03-02 | Passed.
Decodes a given transaction encoded in Amino/Proto base64 bytes, defaulted proto encoding | 2021-03-02 | Passed. | bash-5.0$ pocket-core util decode-tx 1AHbCxcNCjml40SmChR478QRQdzgU9tJc3feErsEFwsKHhIUeO/EEUHc4FPbSXN33hK7BBcLCh4aBzEwMDAwMDASDgoFdXBva3QSBTEwMDAwGmkKJZ1UR3QgBPR/I1XBI8gR+PMwV5vM2CdKkcDX1MLmUdozZw2MgFcSQKXR8qsC/hLMUQpHm57d4Il+aktGpHnDs/it9RT3bOJheBDc1Gz/ZL8xBdYZn3M+ZdVQcSHh/Hyv+2KlYEUKWwgiDUJlIFVuZGVuaWFibGUo8I+nzLaxxsGSAQ== true Type: send Msg: {78EFC41141DCE053DB497377DE12BB04170B0A1E 78EFC41141DCE053DB497377DE12BB04170B0A1E 1000000} Fee: 10000upokt Entropy: -7889434035661191184 Memo: Be Undeniable Signer 78efc41141dce053db497377de12bb04170b0a1e Sig: 04f47f2355c123c811f8f330579bccd8274a91c0d7d4c2e651da33670d8c8057

## Behavioural Tests
Title | Behavioural Tests
Issue | https://github.com/pokt-network/pocket-core/issues/1243
Assignee | Emanuel
Scenarios | Executed On | Status (Pass/Failed/Not Tested) | Results | Code Release Version | Comments | Linked issue (bug)
Make sure TXs are not affected after the upgrade | 2021-03-02 | Passed. |  | RC-0.6.0
Make sure claims are not affected after the upgrade | 2021-03-02 | Passed. |  | RC-0.6.0
Make sure claims are not affected after the upgrade, claims not present | 2021-03-02 | Passed. |  | RC-0.6.0
Make sure unstaked APPs are removed from the state | 2021-03-02 | Passed. |  | RC-0.6.0
Make sure that max age of evidence is enforced in blocks | 2021-03-02 | Passed. |  | RC-0.6.0
Make sure security patch is functional on merkle sum index height | 2021-03-02 | Passed. |  | RC-0.6.0
Make sure security patch is functional on blockhash for height | 2021-03-02 | Passed. |  | RC-0.6.0
Make sure current latest version works even for lower upgradeTX versions | 2021-03-02 | Passed. |  | RC-0.6.0
Make sure that max validator validation/param is working - max validators decreased | 2021-03-02 |  |  | RC-0.6.0
Make sure that max validator validation/param is working - max validators increased | 2021-03-02 |  |  | RC-0.6.0
Make sure that max validator validation/param is working - max validators decreased - node staking | 2021-03-02 |  |  | RC-0.6.0
Make sure that max validator validation/param is working - max validators increased - node staking | 2021-03-02 |  |  | RC-0.6.0
Scenarios Detailing | Executed On | Status (Pass/Failed/Not Tested) | Details | Test result's details
- Make sure security patch is functional on merkle sum index height. - Make sure security patch is functional on blockhash for height. - Make sure claims are not affected after the upgrade - Make sure claims are not affected after the upgrade, claims not present | 2021-03-02 | Passed. | - Upgrade Height set to block 9. | Claims regarding the upgradeHeight (block 9) session: bash-5.0$ pocket-core query node-claim 4fd7bb7c7b62752cb29163ff455ae4d31326c2d3 3aa5afa3a35ab3e2b253516676dddb5b2b6f2f27ef9fe2f894483141dd765d6e relay 0011 9 13 http://localhost:8081/v1/query/nodeclaim { "type": "pocketcore/claim", "value": { "evidence_type": "1", "expiration_height": "213", "from_address": "4fd7bb7c7b62752cb29163ff455ae4d31326c2d3", "header": { "app_public_key": "3aa5afa3a35ab3e2b253516676dddb5b2b6f2f27ef9fe2f894483141dd765d6e", "chain": "0011", "session_height": "9" }, "merkle_root": { "merkleHash": "920zjZQ+HfTboMqwgqXGBd093f3ofs9cLMO4PCZubR4=", "range": { "lower": "0", "upper": "18446613438032496465" } }, "total_proofs": "4217" } }
- PRLTS started on block 2.
|  |  | - Session_block_frequency set to 2. | Balance on Block 16 (after being paid): 10000511105 - Rewarded with +1819 POKTs, regarding 4217 relays served DURING the upgrade height block.
- Claims for session on blocks 4,5; will be sent on block 9 (upgrade height block).
|  |  | - Claims for session on blocks 2,3; will be sent on block 7 ( before upgrade height block). | Balance on Block 16 (after being paid): 10000511105 - Rewarded with +1819 POKTs, regarding 4217 relays served DURING the upgrade height block.
- Claims for session on blocks 8,9 (where Upgrade Height will happen) to be sent on block 12.
- Make sure that max validator validation/param is working - max validators decreased - Make sure that max validator validation/param is working - max validators increased - Make sure that max validator validation/param is working - max validators decreased - node staking - Make sure that max validator validation/param is working - max validators increased - node staking | 2021-03-04 | Passed. | - Network Started with 5 validators. | Start of the network: { "jsonrpc": "2.0", "id": -1, "result": { "block_height": "4", "validators": [ { "address": "498D2F6D8A548CD85B0FBB9C2A9CD95365C30AB1", "pub_key": { "type": "tendermint/PubKeyEd25519", "value": "QIkvx7oCeyHA5D51EPJfb3VT1g8RsYZb2eG7xdFvisY=" }, "voting_power": "5000", "proposer_priority": "9000" }, { "address": "554EF1C6E106ADEE3E889D5E484F790CBE96846C", "pub_key": { "type": "tendermint/PubKeyEd25519", "value": "4bc1S3iyOR/cgghwUebnRME8RGiCDSi2TGd5kPUq/GQ=" }, "voting_power": "3000", "proposer_priority": "3000" }, { "address": "566D6923206F2EB6C490E81EB102567B0F2C07BF", "pub_key": { "type": "tendermint/PubKeyEd25519", "value": "wD5BdXwKiHsD1ialzQrnSiW5WCEFiKX7lXnOxCJfYvE=" }, "voting_power": "4000", "proposer_priority": "6000" }, { "address": "DA0D712E0AD5B37393C022C3333BED46C8667D0A", "pub_key": { "type": "tendermint/PubKeyEd25519", "value": "W9v9rVqy9/3QuBXMD+4uJjJCvNuNsZ2yN2XDzGeBXhI=" }, "voting_power": "1000", "proposer_priority": "-3000" }, { "address": "F81896BE1964DF0537A81274B4D2C9604124449E", "pub_key": { "type": "tendermint/PubKeyEd25519", "value": "RA2HmGNG1/Xt6xKSHWrUeCs9kthDRK/gMCINAgccyK4=" }, "voting_power": "2000", "proposer_priority": "0" } ], "count": "5", "total": "5" } }
- /validators Tendermint endpoint returned the 5 max_validators.
- Param change TX executed at block 11.
|  |  | - After 2-3 blocks, the /validators was changed to 3. The three validators left, were the ones with the higher voting power. | When gov tx succeded and reduced to 3: { "jsonrpc": "2.0", "id": -1, "result": { "block_height": "18", "validators": [ { "address": "498D2F6D8A548CD85B0FBB9C2A9CD95365C30AB1", "pub_key": { "type": "tendermint/PubKeyEd25519", "value": "QIkvx7oCeyHA5D51EPJfb3VT1g8RsYZb2eG7xdFvisY=" }, "voting_power": "5000", "proposer_priority": "13000" }, { "address": "554EF1C6E106ADEE3E889D5E484F790CBE96846C", "pub_key": { "type": "tendermint/PubKeyEd25519", "value": "4bc1S3iyOR/cgghwUebnRME8RGiCDSi2TGd5kPUq/GQ=" }, "voting_power": "3000", "proposer_priority": "-5000" }, { "address": "566D6923206F2EB6C490E81EB102567B0F2C07BF", "pub_key": { "type": "tendermint/PubKeyEd25519", "value": "wD5BdXwKiHsD1ialzQrnSiW5WCEFiKX7lXnOxCJfYvE=" }, "voting_power": "4000", "proposer_priority": "4000" } ], "count": "3", "total": "3" } }
- Queried the param, and was set successfully to three.
- Param change TX executed at block 20, set it back to 5.
- After 2-3 blocks, the /validators was changed to 5. The newly 2 validators added, were the ones added before, with the less voting power.
- Queried the param, and was set successfully to three.
|  | Passed. | - Param change TX executed at block 25, set it to 6.
|  |  | - Created new account, set it as a validator, sent tokens and staked that validator. | bash-5.0$ pocket-core query node c913675a3f68a6a25a21710c46b2858119781fcf http://localhost:8081/v1/query/node { "address": "c913675a3f68a6a25a21710c46b2858119781fcf", "chains": [ "0021" ], "jailed": false, "public_key": "475adce156cd7123c07f6a0a856fd6b76ce52751a305f7d0747fd494dcc7d4f4", "service_url": "http://wetest.dev:8081", "status": 2, "tokens": "15500000000", "unstaking_time": "0001-01-01T00:00:00Z" }
|  |  | - Newly created node, staked and added to the max validators. | New 6th validator added: { "jsonrpc": "2.0", "id": -1, "result": { "block_height": "31", "validators": [ { "address": "498D2F6D8A548CD85B0FBB9C2A9CD95365C30AB1", "pub_key": { "type": "tendermint/PubKeyEd25519", "value": "QIkvx7oCeyHA5D51EPJfb3VT1g8RsYZb2eG7xdFvisY=" }, "voting_power": "5000", "proposer_priority": "23638" }, { "address": "554EF1C6E106ADEE3E889D5E484F790CBE96846C", "pub_key": { "type": "tendermint/PubKeyEd25519", "value": "4bc1S3iyOR/cgghwUebnRME8RGiCDSi2TGd5kPUq/GQ=" }, "voting_power": "3000", "proposer_priority": "8888" }, { "address": "566D6923206F2EB6C490E81EB102567B0F2C07BF", "pub_key": { "type": "tendermint/PubKeyEd25519", "value": "wD5BdXwKiHsD1ialzQrnSiW5WCEFiKX7lXnOxCJfYvE=" }, "voting_power": "4000", "proposer_priority": "16263" }, { "address": "C913675A3F68A6A25A21710C46B2858119781FCF", "pub_key": { "type": "tendermint/PubKeyEd25519", "value": "R1rc4VbNcSPAf2oKhW/Wt2zlJ1GjBffQdH/UlNzH1PQ=" }, "voting_power": "15500", "proposer_priority": "-15593" }, { "address": "DA0D712E0AD5B37393C022C3333BED46C8667D0A", "pub_key": { "type": "tendermint/PubKeyEd25519", "value": "W9v9rVqy9/3QuBXMD+4uJjJCvNuNsZ2yN2XDzGeBXhI=" }, "voting_power": "1000", "proposer_priority": "-4346" }, { "address": "F81896BE1964DF0537A81274B4D2C9604124449E", "pub_key": { "type": "tendermint/PubKeyEd25519", "value": "RA2HmGNG1/Xt6xKSHWrUeCs9kthDRK/gMCINAgccyK4=" }, "voting_power": "2000", "proposer_priority": "1654" } ], "count": "6", "total": "6" } }